## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Team Member | Total Time
1 | Title Page | 0.5 | Day 1: 0.5 | Alexis Strickland | 6.5
2 | Table of Contents | 1 | Day 4: 0.5; Day 15: 0.5 | Dominant Elting | 2
3 | Section 1 Executive Summary with Narrative and Conclusions | 1 | Day 15: 2 | Khadeem Dublin | 4.5
4 | Company Background & Current Environment | 1 | Day 11: 0.5; Day 13: 2 | Ryan McCrary | 5
5 | Problem Analysis (BPA, BPI, BPR) | 1.5 | Day 13: 2 |  | 18 | Total Team Time
6 | Proposed System Objectives and Constraints | 2 | Day 11: 1; Day 14: 2
7 | Expected Benefits | 1 | Day 11: 2
8 | Context Diagram | 2 | Day 8: 3
9 | Use Case Diagram | 2 | Day 8: 2
| Meetings | 40 | Day 1: 1.5; Day 4: 8; Day 8: 6; Day 11: 16; Day 13: 8; Day 14: 6; Day 15: 8; Day 16: 6
Remaining Effort |  | 52 | 50 | 50 | 50 | 41.5 | 41.5 | 41.5 | 41.5 | 30.5 | 30.5 | 30.5 | 11 | 11 | -1 | -9
Ideal Effort |  | 52 | 48.2857 | 44.5714 | 40.8571 | 37.1429 | 33.4286 | 29.7143 | 26 | 22.2857 | 18.5714 | 14.8571 | 11.1429 | 7.4286 | 3.7143 | -1.1546e-14

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
9 | Section 2 Executive Summary with Narrative and Conclusions | 2 | [14 empty] | Alexis Strickland | 12 | bar: Day 12
10 | Use Case Diagram | 2 | Day 7: 0.5; Day 12: 0.5 | Dominant Elting | 9
11 | Supplement Specifications (Non-Functional) | [15 empty] | Khadeem Dublin | 10.5
| ---operational | 2 | Day 8: 1.5 | Ryan McCrary | 11
| ---performance | 2 | Day 8: 0.5; Day 12: 1.5
| ---security | 1
| ---cultural and political | 1 | Day 9: 0.5; Day 12: 1
| Concept Diagram | 0.5 | Day 9: 0.5 |  | 42.5 | Total Team Time
| Meetings | 30 | Day 5: 8; Day 6: 8; Day 8: 8; Day 12: 7; Day 13: 4
Remaining Effort |  | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 32.5 | 24.5 | 24 | 14 | 13 | 13 | 13 | 2 | -2 | -2
Ideal Effort |  | 40.5 | 37.6071 | 34.7143 | 31.8214 | 28.9286 | 26.0357 | 23.1429 | 20.25 | 17.3571 | 14.4643 | 11.5714 | 8.6786 | 5.7857 | 2.8929 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alexis Strickland
Dominant Elting
Khadeem Dublin
Ryan McCrary
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alexis Strickland
Dominant Elting
Khadeem Dublin
Ryan McCrary
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alexis Strickland
Dominant Elting
Khadeem Dublin
Ryan McCrary
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Alexis Strickland
Dominant Elting
Khadeem Dublin
Ryan McCrary
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 18
[18 empty] | Sprint 2 | 42.5
[18 empty] | Sprint 3 | 0
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 60.5 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0