## Sprint 1 Daily SCRUM Standup
Question | Team Member | Week: 01/24/2022-01/30/2022 | [6 empty] | Week: 01/31/2022-02/09/2022
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
What did you do yesterday? | Alexis |  |  | Visited Jack Brown's, Observed manager take inventory, Discussed future plans with the manager |  |  | Created Teams Chat, Gathered Documents together to put into Teams files, Created general notes to gather thoughts of what had been done so far |  |  |  | Brainstormed possible use cases, translated use cases into use case diagram and concept diagram |  |  | Organized deliverables and planned out sprint 1 assignments, started documentation outline, documented system objectives and constraints, completed initial and sprint 1 product backlog |  | Continued documenting system objectives and constraints, started system objectives and constraints slide in powerpoint, worked on project plan | Finished documentation on system objectives and constraints, finished system objectives/constaints and current problems slide in powerpoint, added use case diagram and context diagram into powerpoint | Formatted paper into a Word document that can be zipped with other files, edited current environment portion of the paper, revised scrum meeting notes | I wrapped up the project by downloading our shared files from Teams to my desktop to be able to zip up in time for the presentation. We also finished up any last parts of the presentation needed.
| Dom |  |  | Visited Jack Brown's , checked the resuturant enviroment and looked at some aspects that could possiby be innovated |  |  | We brainstormed and went over the rubric. As well as starting the required documents |  |  |  | Started creating use cases and brainstorm ideas for creating the diagrams |  |  | Brainstormed some key points for problem analysis and started putting some key points down for our powerpoint and our sprint one |  | Went back over the information and finished up problem analysis | Couldnt attend the meeting due to other obligations | Edited problem analysis part of the presentation and paper, started an outline of the team evaluation | Couldnt attend the meeting due to other obligations
| Khadeem |  |  | Unable to attend visit to Jack Brown's due to class schedule |  |  | Brainstormed possible system ideas and got an understanding of all documentation needed and project requirements |  |  |  | Did nothing yesterday. |  |  | Worked on project documentation mainly including table of contents, company background, and current environment. |  | Bulletized company background and company enviornment. | Finished company background and current environment section of documentation | Completed presentation slides for company background and current environment. | Worked on the PSPI and help format presentation
| Ryan |  |  | Visited Jack Brown's, talked to the manager, Adam, and watched him perform their shipping/inventory process. Quickly discovered areas for automation/improvement that we could do for this project. |  |  | Helped discuss our deliverables and began organizing the documents to work on for next meeting |  |  |  | Discussed other use cases, helped transform them into use case diagram and concept diagram |  |  | Finished expected benefits and added it to the powerpoint |  | Planned for the powerpoint presentation in class | Worked on the team charter, touched up the problem analysis | Worked on the team charter and team evaluation | Finished the team charter and worked on the sprint burndown chart as well as the backlog chart. Finished and touched up the powerpoint
What will you work on today? | Alexis |  | We plan on visiting our client, Jack Brown's and ask for approval to use his business for our information systems project. |  |  | I plan on organizing what deliverables we will need for this first sprint, develop a schedule to complete the deliverables, speaking to my group about my personal general notes I developed previously |  |  |  | I plan on completing the use case diagram and concept diagram by the end of the meeting, brainstorm as many use cases as possible to communicate all system objectives. |  |  | I plan on talking with my group about starting the documentation together, I will be mainly looking into the system objectives and constraints in the documentation |  | I plan on putting the system objectives and constraints on the powerpoint, finish the project plan, overlook the paper to be sure our notes are in paragraph form | I plan on completely finishing the system objectives and constraints on both the paper and the powerpoint, modify the paper to be complete for submission, observe the powerpoint for what is missing | Format paper out of Teams into Word document, revise system objectives to not include nonfunctional requirements, revise scrum meeting notes given Dr. Kisling's feedback | I plan on practicing the presentation in preparation for tomorrow, as a the co-product owner, I will be making sure all of our documents are gathered and zipped to submit | Planning on presenting the project during class
| Dom |  | We plan on going to jack browns and wanted to see if we could use |  |  | Want to figure out who is doing what for the project, and the required documents |  |  |  | Want to start working on use cases to create a use case diagram |  |  | Wanted to work with my team to finish the objectives, as well as making sure the backlogs and charts are correct |  | Plan on finishing up problem anaysis and put it on microsoft powerpoint and word | Couldnt attend the meeting due to other obligations | Plan on editing problem analysis part of the presentation | Couldnt attend the meeting due to other obligations
| Khadeem |  | Talk with group about how meeting with Jack Brown's went and start brainstorming project |  |  | Get an understanding and started on project and sprint 1 deliverables specifically |  |  |  | Unable to meet with the group due to being sick |  |  | Work on project documentation mainly including table of contents, company background, and current environment. |  | Brainstorm and finalize bullets on company background and company environment | Put idea bullets for current environment and company background into paragraph form for documentation | Put background and environment documentation into presentation form and work on PSPI | Help with the PSPI, finish up any slides necessary, and make sure this week's presenters are comfortable
| Ryan |  | To meet with the team and manager of Jack Browns and begin the brainstorming process of the project |  |  | To start the deliverables and propose a better meeting plan for next week |  |  |  | I want to work on the concept/use case diagram and take what was said in class and use it for our project. |  |  | To finish the expected benefits and add key points to the powerpoint |  | To touch up the expected benefits and discuss the powerpoint and how I will present in class and start creating the burndown chart | To begin the team charter and touch up the burndown chart and spring backlog | To finish the team charter | I will finish the team charter and practicing for the presentation tomorrow | Planning on presenting the project during class
Do you have any obstacles? | Alexis |  | An obstacle was coordinating a time that the manager would be at the restaurant together with a time that the majority of our group members can attend. |  |  | Once we were brainstorming the basics of what is needed for Sprint 1, we hit a stopping point when thinking about use cases and context diagrams. |  |  |  | One of our use cases involves the employees taking responsibility in tracking inventory. The employees may not have the time to do that regularly, so we would need to ask the manager if he feels like the employees could complete that role. |  |  | We encountered an obstacle of running out of time during our first 2 hours of meeting. We ended up coming back to campus to meet for another 2 hours later in the day, putting in more time than accounted. |  | I was personally having problems converting my bulleted points into paragraph form for the paper. I was trying to avoid my objectives section sounding like it was getting repeated in any other section along with transitioning the paragraphs surrounding it properly | We were discussing our code for HTML for another class leading into this meeting. We were able to transition but had to forcefully focus on our plan to meet over communicating about the previous class. | When formatting the paper after it was completed in Teams, I noticed some parts were shorter than needed. I had to change my plans from revising my system requirements to revising some already completed parts of the paper. | As we were meeting as a group after our classes in the afternoon, we were shifted between multiple classrooms in Bate due to clubs meeting there. This meant we had to disconnect from the computers that had our presentation on it and move somewhere else.
| Dom |  | One obstacle was try to figure out a process that we could automate in the resurnt |  |  | When we were brainstorming for this spirnt, trying to figure out use cases and trying to make sure the process was correct |  |  |  | The team was unfamiliar with using diagrams and neededa refresher on how to us them |  |  | Time constraints for some of us so we wwanted to meet again to make sure everything was done |  | I was having problems with trying to put the right infordmation on the micirsoft word | Time constraints was a huge obstacle, I had to work so I was not able to attend the meeting | One major obstacle is just putting the rquired information that was needed for the slides | Time constraints
| Khadeem |  | Due to my class schedule, I wasnt able to take the initial visit to Jack Browns |  |  | Struggled to obtain a good understanding of the scope of the project, specifically with |  |  |  | Didnt attend class or the meeting as I was under the weather and waiting on covid results to return | [6 empty] | Being proficient in HTML | Time constraints
| Ryan |  | Time scheduling and personal issues |  |  | Needed help with the scope and gist of the entire project |  |  |  | Needed help from Dr. K on how to create a use case diagram, which we never learned |  |  | Time scheduling, we had to come back to campus to meet again |  | Had to leave early for personal reasons | Discussing HTML which none of us are proficient in | Have to cut short meeting due to meeting and personal life. | Had problems with finding right team charter template

## Sprint 2 Daily SCRUM Standup
Question | Team Member | Week: 02/11/2022-02/17/2022 | [6 empty] | Week: 02/18/2022-02/24/2022
|  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
What did you do yesterday? | Alexis |  | Contacted Adam, the manager of Jack Brown's about meeting with him next week to show him our recent work and receive feedback |  |  |  | Created the documents needed for the spint into Teams, discussed creating DFDs for the next meeting | Brainstormed DFDs on a whiteboard and finalized them in Lucidchart |  | Created questions to ask Adam regarding the performance aspect of nonfunctional requirements, talked about changes needed for the DFDs to the group for next sprint, faciltitated the goal for the meeting with Adam since I would not be able to meet with him. |  |  |  | Inserted the updated use case diagram and concept diagram into powerpoint, converted notes from Adam to performance requirements, put all nonfunctional requirements in table in documentation, wrote about new documentation, updated project plan, updated sprint 2 backlog, insert product backlog and sprint 2 backlog into powerpoint | I downloaded the documentation to change formatting to transition our document from academic to business form, check through the daily scrum meeting file, check through the burndown chart, check through the backlogs, uploaded files to GitHub
| Dom | [12 empty] | Worked on parts of the team evaluation as well as the helping with the non-functional requirments
| Khadeem | [5 empty] | Yesterday we completed estimating times for burndown chart, delegated task for sprint 2, | Brainstorming and forming data flow diagrams |  | Completed cultural/political requirements, prepared questions to ask Adam |  |  |  | Completed the executive summary | Prepare to present, burndown chart,
| Ryan |  |  |  |  | Created a quick template for the website/working system we will be using | Came up with PSPI, discussed burndown chart | Discussed DFDs |  | Created a first rough draft for our DFDs and finished the operational nonfunctional requirements |  |  | Met with Adam, the manager, to go over nonfunctional requirements and ask more questions regarding the project. | Worked on the team evaluation, PSPI, powerpoint, and documentation | Finalized powerpoint, finished evaluation and section of documentation
What will you work on today? | Alexis |  |  |  |  | I plan on starting the new sprint documents, creating the outlines of the paper and powerpoint, implement changes on the concept diagram, start brainstorming with group on DFDs | I plan on creating and finishing our DFDs in preparation for class tomorrow |  | I plan on discussing the changes needed for our DFDs, brainstorm questions to ask Adam on Monday, come up with probable nonfunctional requirements for the performance section |  |  |  | I plan on converting information given from Adam to the powerpoint, converting answers to performance questions into listed nonfunctional requirements, and change the format of the documentation relating to feedback | I plan on finalizing my hours into the burndown chart, double check with the team that everything in the powerpoint and documentation is there, download the documentation and format according to feedback, help with practice presentation, and upload all files to GitHub. | Day of Presentation
| Dom |  |  |  |  | Today , I would want to work on trying to create dfds as well get started on brainstorming for some of nonfuctional requirements for the sprint | Got together to work on more of the nonfuctional requirerments. |  | Plan on trying to fixing some our mistakes for the dfds and finishing up our requirements |  |  |  |  | Want to finish up the presentationa and get ready for tomorrow | Day of Presentation
| Khadeem |  |  |  |  | Today I plan on updating and making corrections to sprint 1 and the case diagrams, estimating burndown chart times, and gaining a grasp on everything needed for sprint 2. | Plan to help complete dfd's |  | Help complete Dfds, non-functional requirements and prepare to meet with adam |  |  |  | Recap on our meeting with Adam. Work on the executive summary, and finalize the cultutral and political requirements | Prepare for presentation, and finalize powerpoint | Day of Presentation
| Ryan |  |  |  |  | Today I will work on the PSPI code, which will show us an early model for our working system, and help with DFDs | To start with the DFDs |  | Help create DFDs as well as the operational section for the nonfunctional requirements |  |  |  | Will work on the powerpoint, documentation, and PSPI | Finish the powerpoint, evaluation, and part of documentation | Day of Presentation
Do you have any obstacles? | Alexis |  |  |  |  | The main constraint being that it had been a few days since contacting Adam and trying to decide when to contact him again. | Working on the DFDs for next sprint to bring to class when we had not finished our nonfunctional requirements for this sprint yet |  | Not being able to attend the meeting with Adam and being sure that our questions were prepared beforehand and asking the correct information |  |  |  | Wednesday and Thursday I have a collection of 2 exams and 2 projects including this sprint, which has been in the way of focusing on this sprint | The web design project pushed our meeting a little later than planned
| Dom |  |  |  |  | Getting in contact with the manager to try to figure out a more accurate despription of what he wants |  |  | Just the fact of the manager is just taking so long to reply so we just have to find the right time to meet so that we can figure out some of the requirments |  |  |  | Had so much projects and work to do, could not find a time to meet with the team | A lot going on with other classes
| Khadeem |  |  |  |  | Time constraints | Still havent got a response from product owner | [5 empty] | Course workload this week is hectic and large numerous assignments in other classes. | Web app project due today/ Limited availability and time today
| Ryan |  |  |  |  | Having little knowledge with HTML/PHP |  |  | Struggling with formatting the DFDs, making sure they flowed correctly and efficiently |  |  |  | The obstacles I have are the Web Application Project for MIS 4153 | MIS 4153 project due today

## Sprint 3 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/2022-xx/xx/2022 | [6 empty] | Week: xx/xx/2022-xx/xx/2022
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 4 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/2022-xx/xx/2022 | [6 empty] | Week: xx/xx/2022-xx/xx/2022
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 5 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/2022-xx/xx/2022 | [6 empty] | Week: xx/xx/2022-xx/xx/2022
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 6 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/2022-xx/xx/2022 | [6 empty] | Week: xx/xx/2022-xx/xx/2022
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?